## Sheet 1
Work Break Down Structure
Main Category - WBS1 | Sub Category - WBS2 | Activity
Safety On Work Sites | Safety | Barriers and signs are erected and used as required to protect the safety of site personnel and the public
Safety On Work Sites | Safety | Check & maintain barrier fencing / hoardings
Safety On Work Sites | Safety | Check safety nets
Safety On Work Sites | Scaffolding | Erect alibaba scaffold
Safety On Work Sites | Scaffolding | Erect H frame
Safety On Work Sites | Tool Box Talks | Attend tool box talks
Safety On Work Sites | Tool Box Talks | Maintain hand tools
Preliminaries | Site Establishment | Set up Fencing / Hoardings / Gantries
Preliminaries | Site Establishment | Set up safety management systems
Preliminaries | Site Establishment | Temp stair access construct / fit
Preliminaries | Site Set Out | Locate boundaries and set up off set lines
Preliminaries | Site Set Out | Rough set out and construct profiles
Preliminaries | Leveling | Set laser level, determine plumb / straight
Preliminaries | Leveling | Set up theodolite, determine heights
Preliminaries | Demolition | Break out concrete
Preliminaries | Demolition | Concrete cutting
Preliminaries | Sub Trades | Checking completed works foundation
Preliminaries | Sub Trades | Checking completed works interior
Supervision / Education | Skills Maintenance | Attending Presentations and Tutorials
Supervision / Education | Skills Maintenance | Subscribing to a trade Magazine
Supervision / Education | Site Safety | Supervised others
Supervision / Education | Preliminaries | Demonstrated processes
Foundations | Formwork | Insitu propping / false work
Foundations | Formwork | Pads
Foundations | Formwork | Peg, plank, temp brace & cleat / fix
Floor Systems | Suspended Timber Floors | Joist blocking / dwangs / cut / fix
Floor Systems | Suspended Timber Floors | Place & fix boundary joists
Floor Systems | Ramps | Erect false work timber
Floor Systems | Concrete Stairs | Construct carriage / soffit formwork
Floor Systems | Concrete Stairs | Drill & epoxy adhesive starters / dowels
Structures | Timber Framing | Blocking
Structures | Timber Framing | Brace element fixings
Structures | Timber Framing | Raking Plates
Structures | Timber Framing | Set out on floor using documentation
Structures | Timber Framing Prenail | Set out floor using documentation
Structures | Metal Framing | Cut out door ways
Structures | Metal Framing | Fix wall junctions
Structures | Precast Concrete | Locate & place inserts
Structures | Precast Concrete | Place edge formers
Structures | Structural Steel | Place steel bracing frames
Structures | Structural Steel | Portal frames
Structures | Insitu Concrete | Erect false work metal
Structures | Insitu Concrete | Erect false work timber
Roof Structures | Timber Trusses | Brace element installed
Roof Structures | Timber Trusses | Ceiling battens / metal
Roof Structures | Metal Trusses | Fit hip & valley rafters
Roof Structures | Metal Trusses | Fly rafters
Roof Structures | Metal Trusses | Gable framing
Roof Structures | Pitched Roofs | Cut / fix ceiling joist
Roof Structures | Pitched Roofs | Cut / fix ceiling runners / soldiers
Roof Structures | Commercial Gutters | Prepare work area / set up working platform
Roof Structures | Commercial Gutters | Set out grade / stringer / ribbon board
Roof Structures | Flat Roofs | Cut / fix soffit bearers / sprockets
Roof Structures | Flat Roofs | Cut & fix drip flashings
Exterior Envelope | Cavity Systems | Moulseal to found rebate
Exterior Envelope | Cavity Systems | Polystyrene sheet
Exterior Envelope | Exterior Joinery | Glazing to frames
Exterior Envelope | Exterior Joinery | Head flashings
Exterior Envelope | Cladding | Isolating membrane
Exterior Envelope | Cladding | Light Curtain Wall Cladding Systems (NoteType)
Exterior Envelope | Roofing | Down pipes cut & fix with brackets
Exterior Envelope | Roofing | Drip flashings fit
Interior Finishings | Straightening | Replacing studs
Interior Finishings | Straightening | Strapping secondary studs
Interior Finishings | Thermal Insulation | Double glazing / retro fit
Interior Finishings | Thermal Insulation | Fibre glass segment cut / fit
Interior Finishings | Sound Insulation | Sheet linings installed
Interior Finishings | Sound Insulation | Sound insulation segment cut / fit
Interior Finishings | Internal Linings | Ply / MDF profiled sheet cut / fix
Interior Finishings | Internal Linings | Ply / MDF sheet cut / fix / notes
Interior Finishings | Joinery | Cavity sliders assembled / fit
Interior Finishings | Joinery | Door frames cut / assembled / fit
Interior Finishings | Hardware | Door latch sets, set out / fit
Landscaping / Site Works | Driveways / Paths | Concrete paced / compacted
Landscaping / Site Works | Driveways / Paths | Cut, bend, place & tie reinforcing
Landscaping / Site Works | Fencing | Gates construct / brace
Landscaping / Site Works | Fencing | Hang gates
Landscaping / Site Works | Retaining Walls | Chair reinforcing
Landscaping / Site Works | Retaining Walls | Concrete finished / plain
Landscaping / Site Works | Retaining Walls | Concrete placed / compacted
Landscaping / Site Works | Retaining Walls | Excavate holes / trenches
Landscaping / Site Works | Retaining Walls | Filter cloth place
Landscaping / Site Works | Pergolas | Beams cut / fix / notes
Landscaping / Site Works | Pergolas | Bracing fitted
Landscaping / Site Works | Decks | Cut piles to height
Landscaping / Site Works | Decks | Decking set out / cut / fix
Landscaping / Site Works | Decks | Joists set out / cut / fix
Landscaping / Site Works | Paving | Mowing strips set on concrete
Landscaping / Site Works | Paving | Pavers compacted